SecureHITL-Trade

4-Week Sprint Plan  |  Team of 3

| Shreya Frontend (React) + Testing | Chethan ML + Signal Engine + Infra + Docs | Dharshini Backend + Auth + FastAPI |
| --- | --- | --- |

# Project Overview

SecureHITL-Trade is a hybrid Copilot-to-Autopilot trading framework. The four-week sprint is structured into three development phases followed by a final integration and delivery phase. Each day has clearly scoped tasks and end-of-day deliverables to ensure parallel progress across all three workstreams.

## Phase Summary

| Phase | Timeline | Focus |
| --- | --- | --- |
| Phase 1 | Week 1 (Days 1–5) | Foundation — project scaffolding, base FastAPI, DB schema, React shell, core ML pipeline |
| Phase 2 | Week 2 (Days 6–10) | Core Features — signal engine, XAI engine, trading UI, WebSocket, JWT auth |
| Phase 3 | Week 3 (Days 11–15) | Advanced Features — Autopilot mode, Hijack panel, guardrails, E2E tests |
| Phase 4 | Week 4 (Days 16–20) | Integration, Testing & Delivery — full integration, report writing, paper trading demo |

Daily commitment: ~2–3 hours per person. Tasks are parallelised to avoid bottlenecks. Each phase ends with an integration checkpoint.

| PHASE 1 | Foundation ¦ Week 1 (Days 1 – 5) |
| --- | --- |

Goal: All three workstreams running simultaneously. By end of Day 5 — a working React app, a live FastAPI server connected to PostgreSQL, and a validated ML signal pipeline.

| Day | Shreya — Frontend + Testing | Chethan — ML + Signal Engine + Infra + Docs | Dharshini — Backend + Auth + FastAPI |
| --- | --- | --- | --- |
| Day 1 | Scaffold Vite + React + Tailwind project Set up folder structure: pages/, components/, hooks/, services/ Create placeholder routes (/, /dashboard, /proposals, /hijack) Push to repo, confirm CI passes | Set up Python ML project structure (ml/, engine/, utils/) Implement OHLCV data loader from Alpaca / CSV sim Set up virtual env, requirements.txt Set up Docker Compose skeleton (db + api + redis services) | Scaffold FastAPI project structure (routers/, models/, schemas/, core/) Create /health and /version endpoints Initialise PostgreSQL + SQLAlchemy ORM Define User, TradeProposal, AuditLog models + first Alembic migration |
| Day 2 | Build AppShell: Sidebar navigation + TopBar component Implement React Router with lazy-loaded pages Create base UI tokens (colors, typography) in Tailwind config Dark/light mode toggle | Implement RSI, MACD, Bollinger Bands, EMA (pandas-ta) Signal engine: combine indicators → BUY/SELL/HOLD output Return signal + indicator values as dict Write pytest: signal output shape + value ranges | Implement JWT auth: register + login endpoints bcrypt password hashing, JWT token generation + validation Auth middleware (FastAPI dependency injection) Write pytest tests: register, login, invalid token |
| Day 3 | Build ProposalCard component (static mock data) ProposalCard props: symbol, signal, XAI reason, qty, SL, TP, actions Add Approve / Reject button handlers (stub) Recharts price chart component (static OHLCV) | XAI engine skeleton: indicator dict → natural language justification Rule-based template: 'RSI at X, MACD crossed Y, signal is BUY because...' Pytest: XAI output is non-empty string for all signal types Docker Compose: add Redis service, confirm container starts | Wire auth middleware to all protected routes POST /trade/propose — accept signal payload, store in DB GET /trade/proposals — paginated list endpoint Test via Postman / HTTPie, document in route comments |
| Day 4 | useWebSocket hook: connect to WS server, auto-reconnect logic Pipe mock WS messages into ProposalCard (live render test) P&L summary card component (mock numbers) Responsive layout: mobile breakpoints for dashboard | Redis Pub/Sub setup: publish signal events from signal engine WebSocket server endpoint /ws (FastAPI + Redis listener) Broadcast trade proposals via Redis → WS clients Docker Compose: add nginx service skeleton | PATCH /trade/{id}/action — approve/reject endpoint Audit log entry on every action (timestamp + user_id) GET /audit/log — paginated audit trail Confirm DB writes work end-to-end with Postman |
| Day 5 | Phase 1 integration: connect ProposalCard to live /trade/proposals API Wire Approve/Reject buttons to PATCH /trade/{id}/action End-to-end smoke test: login → see proposal → approve Write Vitest tests for ProposalCard (render + click) | Nginx reverse proxy config: route /api → FastAPI, /ws → WebSocket Docker Compose v1: full stack startup test (db, api, redis, nginx) Confirm signal engine output reaches WS client via Redis Pub/Sub Write developer README: how to run full stack locally | POST /signal/generate route — accepts symbol, calls signal engine, stores result Return signal + XAI justification from engine to frontend Validate route schema with Pydantic models Phase 1 checkpoint: full login → proposal → approve flow working |

## Phase 1 — End of Week Deliverables

| Owner | Deliverable |
| --- | --- |
| Shreya | Running React app with navigation, ProposalCard UI, WebSocket hook, and Vitest suite |
| Chethan | Signal engine (RSI/MACD/BB/EMA), XAI template, Redis Pub/Sub, Docker Compose v1 + Nginx skeleton |
| Dharshini | FastAPI scaffold, PostgreSQL + Alembic, JWT auth, /trade and /audit routes working |
| All | Full login → proposal → approve/reject flow working end-to-end on localhost |

| PHASE 2 | Core Features ¦ Week 2 (Days 6 – 10) |
| --- | --- |

Goal: Build the full Copilot (HITL) mode. By end of Day 10 — live trade proposals with XAI justification, approve/reject/modify flow, P&L audit trail, and Alpaca paper trading all wired together.

| Day | Shreya — Frontend + Testing | Chethan — ML + Signal Engine + Infra + Docs | Dharshini — Backend + Auth + FastAPI |
| --- | --- | --- | --- |
| Day 6 | Login + Register pages with form validation (react-hook-form) Auth context + JWT storage in httpOnly cookie Protected route wrapper component Redirect to /dashboard after login | Multi-symbol scanner: scan list of tickers every 60s (asyncio background task) Emit Redis event on signal change for each symbol Add confidence_score (0–1) to signal output Docker Compose: health checks for all services | Rate limiting middleware (slowapi) on all API routes CORS policy + security headers middleware (CSP, X-Frame-Options) GET /user/me — return current user profile Error handling middleware: standardised JSON error responses |
| Day 7 | HijackPanel component shell: SL/TP/Qty editable fields Form state management + validation (positive numbers, SL < entry price) Disable submit until all fields valid Unit test: HijackPanel renders + validates correctly | XAI engine upgrade: sklearn logistic regression on indicator features Train on synthetic OHLCV data, save model.pkl Predict probability of signal success, include in XAI output Pytest: model loads and predicts for any valid indicator dict | POST /trade/{id}/override — accept modified SL/TP/qty Server-side override validation (guardrail checks via Pydantic) Log override event in audit table (status → OVERRIDDEN) Pydantic schema for override request + response |
| Day 8 | Recharts price chart: live OHLCV from /market/ohlcv endpoint Overlay RSI subplot below price chart Chart time-range selector (1D, 1W, 1M) Test: chart renders without errors for all ranges | Alpaca paper trading integration: alpaca-trade-api Python SDK setup AlpacaExecutor class: submit BUY/SELL orders, poll status Mock Alpaca response for local dev (env flag) Pytest: executor submits order and returns fill status | POST /trade/execute — call AlpacaExecutor, update trade status in DB GET /market/ohlcv — fetch from Alpaca data API, cache in Redis (TTL 60s) WebSocket: push OHLCV tick updates to connected clients Test: repeated calls use Redis cache, not repeated Alpaca API calls |
| Day 9 | P&L dashboard card: daily P&L, win rate, trade count Audit log page: table of all actions with filters (date, symbol, action type) Export audit log as CSV (client-side) Test: CSV export downloads correct data | Guardrail engine: max position size, daily loss limit, max open trades Guardrail config stored in JSON / env, loaded at startup Block execution if any guardrail breached, return reason string Pytest: each guardrail condition fires correctly | GET/PUT /guardrails/config — expose guardrail thresholds via API Admin endpoint: GET /admin/users (JWT role check) Full audit schema: add metadata columns (mode, override_delta, guardrail_hit) Postman collection: export all endpoints so far |
| Day 10 | Phase 2 integration test: full Copilot flow end-to-end Test: login → live proposal arrives → modify in HijackPanel → approve → order executes Vitest: 5 new component tests (HijackPanel, AuditLog, Chart, P&L card, ProtectedRoute) Fix any UI bugs found during integration | Intervention Hijack logic: re-validate signal with overridden params Return updated XAI justification reflecting override values Pytest: override changes XAI output correctly Docker Compose v2: confirm full stack starts cleanly with all services | Wire /trade/execute to guardrail check before calling Alpaca API docs: complete OpenAPI docstrings for all routes Phase 2 checkpoint: all services communicate correctly Chapter 3 (System Design) first draft: architecture + component descriptions |

## Phase 2 — End of Week Deliverables

| Owner | Deliverable |
| --- | --- |
| Shreya | Complete Copilot UI: login, live proposals, HijackPanel, P&L card, audit log + Vitest tests |
| Chethan | ML-backed XAI engine, multi-symbol scanner, Alpaca executor, guardrail engine, Docker v2 |
| Dharshini | Security layer (rate limit, CSP, CORS), full audit schema, /execute + /override routes, OpenAPI docs |
| All | Copilot (HITL) mode fully functional with paper trading, live WebSocket, and override flow |

| PHASE 3 | Advanced Features ¦ Week 3 (Days 11 – 15) |
| --- | --- |

Goal: Build Autopilot (HOTL) mode, complete the Intervention Hijack, harden security, and achieve comprehensive test coverage. By end of Day 15 both modes must work simultaneously.

| Day | Shreya — Frontend + Testing | Chethan — ML + Signal Engine + Infra + Docs | Dharshini — Backend + Auth + FastAPI |
| --- | --- | --- | --- |
| Day 11 | Autopilot mode toggle UI: switch in TopBar, persists to backend Visual indicator: COPILOT (teal) vs AUTOPILOT (amber) badge Mode-aware rendering: in Autopilot, proposals auto-collapse with override button only Test: toggle changes mode state and badge correctly | Autopilot execution flow: if mode=AUTOPILOT and guardrails pass, auto-execute Emit WebSocket event on auto-execution for UI to reflect Log auto-execution in audit table with mode=AUTOPILOT flag Pytest: autopilot executes only when all guardrails pass | PATCH /user/mode — store COPILOT/AUTOPILOT per user in DB Mode embedded in JWT claims (token refresh on toggle) FastAPI dependency: mode-aware route guards Project report: Chapter 4 (Implementation) first draft |
| Day 12 | HijackPanel: wire to live /trade/{id}/override endpoint Real-time feedback: spinner + success/error toast after submission If autopilot active, Hijack button interrupts and pauses execution Test: hijack interrupt sets proposal status to PAUSED | Autopilot interrupt: handle INTERRUPTED status — halt execution, notify via WS Recalculate signal after hijack params applied Autopilot resumes only on user confirm or configurable timeout Pytest: interrupt pauses execution, resumes on confirm | POST /trade/{id}/interrupt — pause autopilot execution, set status PAUSED POST /trade/{id}/resume — resume after hijack review Guardrail breach notification via WebSocket to frontend Chapter 4: sequence diagrams for Copilot and Autopilot flows |
| Day 13 | Pytest TC-01 to TC-06: API integration tests (login, propose, approve, reject, override, autopilot toggle) Test environment: pytest fixtures, test DB (SQLite in-memory) GitHub Actions CI workflow: run pytest on push All 6 tests passing in CI | Signal engine backtest: 30-day historical Alpaca data Compute precision/recall for BUY/SELL signals Save backtest results to JSON, expose GET /signal/backtest-report Docker Compose production profile: env vars from .env.prod | TLS: self-signed cert setup for localhost dev (documented) Nginx SSL termination config Chapter 5 (Testing & Results): draft test methodology section API user guide: document all endpoints with request/response examples |
| Day 14 | Pytest TC-07 to TC-12: WebSocket reconnect, guardrail breach UI, mode toggle, HijackPanel validation, CSV export, chart range Fix any flaky tests, target 100% pass rate Vitest coverage report: target >80% component coverage Document test cases in TC table for report | Alpaca paper trading: test 5 live symbols over 1 trading session Log results: fills, partial fills, rejections Tune guardrail thresholds based on paper trading results Update XAI justification templates for edge cases (neutral, high volatility) | OWASP input validation on all POST/PATCH endpoints bandit security scan on Python codebase, fix critical issues Chapter 6 (Conclusion + Future Work) first draft Landing page HTML skeleton for user guide site |
| Day 15 | Phase 3 integration: full E2E test of both Copilot and Autopilot modes TC table: fill expected vs actual results for all 12 test cases Final Vitest run: document pass/fail stats UI polish: loading skeletons, empty states, error boundaries | Full docker compose up smoke test: all services start, all health checks green Signal engine: add EMA crossover as fourth indicator combination Finalise model.pkl, confirm it loads correctly inside Docker container Write developer README: signal engine, how to add new indicators | Confirm all FastAPI routes return correct status codes and Pydantic-validated responses Final Alembic migration: ensure schema matches all feature additions Phase 3 checkpoint: both modes working, all tests passing, Docker stack healthy Chapter 3 & 4 final revisions |

## Phase 3 — End of Week Deliverables

| Owner | Deliverable |
| --- | --- |
| Shreya | TC-01 to TC-12 all passing; Vitest >80% coverage; Autopilot/Copilot toggle UI; E2E results table |
| Chethan | Autopilot execution + interrupt; backtest report; EMA crossover; production Docker Compose; paper trading validated |
| Dharshini | Interrupt/resume routes; security hardened (OWASP + bandit); Chapter 3/4/5 drafts; API user guide; Nginx SSL |
| All | Both HITL and HOTL modes working end-to-end with tests, Docker, and Alpaca paper trading |

| PHASE 4 | Integration, Report & Delivery ¦ Week 4 (Days 16 – 20) |
| --- | --- |

Goal: Code freeze, complete documentation, produce the final demo recording, and submit the full project report. No new features — only fixes, polish, and documentation.

| Day | Shreya — Frontend + Testing | Chethan — ML + Signal Engine + Infra + Docs | Dharshini — Backend + Auth + FastAPI |
| --- | --- | --- | --- |
| Day 16 | Final UI pass: consistent spacing, colors, typography across all pages Landing / login page styling polish Generate Vitest HTML coverage report, screenshot for report Write frontend README: setup, run, test instructions | Code freeze for ML pipeline Confirm model.pkl loads in clean Docker env Tag release: v1.0.0 on GitHub Update Docker Compose: ensure images build from scratch on clean machine | Merge all branches to main, resolve any conflicts Run full pytest suite on main branch, fix any regressions Final Postman collection export: all API endpoints Final OpenAPI schema review: ensure all routes are documented |
| Day 17 | Record demo video: Copilot mode flow (5 min) Screen capture: login → signal arrives → XAI reason displayed → modify SL/TP → approve → order fills Write user guide section: How to use Copilot mode Review Chethan's Chapter 3 system design diagrams | Record demo video: Autopilot mode + Hijack interrupt (5 min) Screen capture: Autopilot auto-executes → user hits Hijack → modifies → resumes Write developer guide: signal engine, guardrail config, adding new indicators Combine all report chapters into final Kerdostat.docx | Add all screenshots, architecture diagrams, sequence diagrams to report Format references section (IEEE style) Write abstract + executive summary final versions Review and edit Chapter 4 implementation section |
| Day 18 | Proof-read Chapter 5 (Testing): verify TC table matches actual test results Add Vitest coverage screenshot to report Complete frontend component documentation (JSDoc comments) Final check: all Vitest tests pass on clean install | Proof-read Chapter 4 (Implementation): verify all code snippets correct Add signal engine accuracy table (precision/recall) to report Add backtest results chart screenshot to report Final Docker Compose smoke test | Final report formatting: consistent heading levels, page numbers, TOC Print-quality check: all tables fit within page margins Plagiarism check if required Submit checklist: report, repo link, demo video links |
| Day 19 | Buffer: fix any bugs found during report review Re-run full Vitest suite, update TC table if needed Ensure GitHub repo is clean: .gitignore correct, no secrets committed Add LICENSE file | Buffer: fix any infra/Docker issues found during report review Ensure all environment variables documented in .env.example Update CHANGELOG.md Final signal engine test in Docker container | Buffer: final report revisions from team feedback Final API endpoint test via Postman collection Update README: project overview, team, setup instructions Prepare submission package: zip repo + report + demo links |
| Day 20 | Final sign-off: confirm Vitest suite passes on latest main Review complete submission package Submit | Final sign-off: Docker Compose starts cleanly, all health checks green Review complete submission package Submit | Final sign-off: pytest suite passes, all routes respond correctly Final report PDF export and review Submit all deliverables: code, report, demo |

## Phase 4 — Final Deliverables

| Owner | Deliverable |
| --- | --- |
| Shreya | Copilot demo video; Vitest HTML coverage report; frontend README; TC table finalised |
| Chethan | Autopilot + Hijack demo video; backtest accuracy table; developer guide; v1.0.0 tagged; Docker final |
| Dharshini | Complete project report (all chapters); Postman collection; submission package; all pytest passing |
| All | Submitted: GitHub repo + final report + demo videos + Postman collection |

# Responsibility Matrix

Full mapping of every system component to its owner.

| Component | Shreya | Chethan | Dharshini |
| --- | --- | --- | --- |
| React App (Vite + Tailwind) | ✅ Owner |  |  |
| All Page Components + Routing | ✅ Owner |  |  |
| ProposalCard (XAI display, qty edit, actions) | ✅ Owner |  |  |
| HijackPanel (editable SL/TP/qty) | ✅ Owner |  |  |
| Recharts Price Chart + P&L Card | ✅ Owner |  |  |
| useWebSocket Hook + Auto-reconnect | ✅ Owner |  |  |
| pytest TC-01 to TC-12 | ✅ Owner |  |  |
| Vitest Frontend Component Tests | ✅ Owner |  |  |
| ML Signal Engine (RSI/MACD/BB/EMA) |  | ✅ Owner |  |
| XAI Justification Engine |  | ✅ Owner |  |
| Guardrail Engine |  | ✅ Owner |  |
| Background Scanning Loop (asyncio) |  | ✅ Owner |  |
| Autopilot Mode Execution Flow |  | ✅ Owner |  |
| Intervention Hijack Logic |  | ✅ Owner |  |
| Alpaca Paper Trading Integration |  | ✅ Owner |  |
| Redis Pub/Sub + WebSocket Server |  | ✅ Owner |  |
| Docker Compose + Nginx Config |  | ✅ Owner |  |
| Project Report (all chapters) |  | ✅ Owner |  |
| Developer Guide + README |  | ✅ Owner |  |
| FastAPI App + SQLAlchemy ORM + Alembic |  |  | ✅ Owner |
| PostgreSQL Schema + Audit Logger |  |  | ✅ Owner |
| JWT Auth (register, login, middleware) |  |  | ✅ Owner |
| All API Route Handlers (/trade, /audit, /market…) |  |  | ✅ Owner |
| Pydantic Schemas + Request/Response Validation |  |  | ✅ Owner |
| Security (bcrypt, rate limiting, TLS, CSP) |  |  | ✅ Owner |
| OpenAPI Docs + Postman Collection |  |  | ✅ Owner |
| API User Guide + Landing Page |  |  | ✅ Owner |

SecureHITL-Trade  |  4-Week Sprint Plan  |  Generated for team planning purposes